## Slide 1: Formal sector
October 2020
Activity Report

## Slide 2: October 2020 activities
Contract activities:
Quarterly report sent to digital square
Requirement Design documents Updated on the wiki.
  https://openimis.atlassian.net/wiki/spaces/OP/pages/1730740225/Formal+Sector+Modules+in+development
  Acceptance test cases published, feedback requested from Nepal, Djibouti and Myanmar
Shell backend modules Delivered:
  Policy Holder
  Contribution plan and bundle
  Contract (aka contribution collection)
Scope activities:
Calculation and Profile Module designed
Backends development on going
  Contract (graphQL, mutations)
  Contribution plan and bundle (graphQL, mutations)
  Policy holder (graphQL)
Issues
Team will be complete only this month of November, among other reasons, this prevented to deliver the frontend on the 31/10 as per contract
Extension a amendment of the contract still not done

## Slide 3: Future activities for November
Contract activities:
Next due date on 31/12
Development activities:
Backend module development
  Contribution plan and bundle (finishing mutation, implementing authorities)
  Contract (finishing graphQL, mutations and authorities)
  PolicyHolder (graphQL, mutations and authorities)
Frontend module development.
  Contribution plan and bundle
  PolicyHolder*

## Slide 4: State of deliverables
Activity | Deliverable | Due Date | Updated due dates
0.1 | Requirements definition document | Delivered | 
0.2 | Conceptual design document | Delivered | 
1.1 | Frontend and backend for the “Policy holder” module & quarterly narrative report | December 31, 2020 | December 31, 2020
1.2 | Backend for the “Contract” ( previously “Contribution Collection” ) module | February 28, 2021 | December 31, 2020
1.3 | Frontend module for the “Policy Holder Portal” | February 28, 2021 | February 28, 2021
1.4 | Frontend for the “Contract” (previously “Contribution Collection” ) module | February 28, 2021 | December 31, 2020
2.1 | Frontend and backend for the “Contribution plan and Contribution plans bundle” module | October 31, 2020 | February 28, 2021
2.2 | Frontend and backend for the “Calculation” module | October 31, 2020 | February 28, 2020
3 | Frontend and backend the “Profile” module | December 31, 2020 | February 28, 2020
4.1 | Early delivery of the Shell backend modules (“Policy holder”, “Contribution Collection”, “Contribution plans” ), | Delivered | 
4.2 | reviewed Healthix FIHR documents | December 31, 2020 | December 31, 2020

## Slide 5: Formal Sector