## Slide 1: Formal sector
December 2020
Activity Report

## Slide 2: Roadmap

## Slide 3: November 2020 activities
Scope activities:
PolicyHolder be module done
PolicyHolder fe module 70% done
Contribution plan module details design finished
Other activities
On-boarding of new members
Defining some of the overall “tools” like Models , standard mutations took time

## Slide 4: Future activities for December
Contract activities:
Next due date on 31/12
Development activities:
Backend module development
  Contribution plan and bundle (finishing mutation, implementing authorities)
  Contract (finishing graphQL, mutations and authorities) (at risk)
Frontend module development.
  PolicyHolder*
  Contribution plan and bundle
  Contract (at risk)

## Slide 5: State of deliverables
Activity | Deliverable | Due Date | Updated due dates
0.1 | Requirements definition document | Delivered | 
0.2 | Conceptual design document | Delivered | 
1.1 | Frontend and backend for the “Policy holder” module & quarterly narrative report | December 31, 2020 | December 31, 2020
1.2 | Backend for the “Contract” ( previously “Contribution Collection” ) module | February 28, 2021 | December 31, 2020
1.3 | Frontend module for the “Policy Holder Portal” | February 28, 2021 | February 28, 2021
1.4 | Frontend for the “Contract” (previously “Contribution Collection” ) module | February 28, 2021 | December 31, 2020
2.1 | Frontend and backend for the “Contribution plan and Contribution plans bundle” module | October 31, 2020 | February 28, 2021
2.2 | Frontend and backend for the “Calculation” module | October 31, 2020 | February 28, 2020
3 | Frontend and backend the “Profile” module | December 31, 2020 | February 28, 2020
4.1 | Early delivery of the Shell backend modules (“Policy holder”, “Contribution Collection”, “Contribution plans” ), | Delivered | 
4.2 | reviewed Healthix FIHR documents | December 31, 2020 | December 31, 2020

## Slide 6: PolicyHolder Screens: Search

## Slide 7: PolicyHolder Screens: Card

## Slide 8: PolicyHolder Screens: Insuree

## Slide 9: PolicyHolder Screens: add Insuree

## Slide 10: PolicyHolder Screens: Edit Insuree

## Slide 11: PolicyHolder Screens: Delete Insuree

## Slide 12: PolicyHolder Screens: Contribution Plan Bundle

## Slide 13: PolicyHolder Screens: User

## Slide 14: Formal Sector