## Slide 1: Formal sector
March 2020
Activity Report

## Slide 2: Roadmap

## Slide 3: March 2021 activities
Scope activities:
Calculation FE/BE finished
Contract BE/FE finished
Profile BE finished
Profile FE 40% done
Time reporting
Soldevelo 315 MD
SwissTPH 60 Days
Note: Time reporting activation on JIRA

## Slide 4: Future activities for April
Contract activities:
Delivery of Profile and Policyholder portal on the 06/05
Development activities:
Backend module development
  PolicyHolder Portal
Frontend module development.
  PolicyHolder Portal
  Profile

## Slide 5: State of deliverables
Activity | Deliverable | Due Date
0.1 | Requirements definition document | Delivered
0.2 | Conceptual design document | Delivered
1.1 | Frontend and backend for the “Policy holder” module & quarterly narrative report | Delivered
1.2 | Backend for the “Contract” ( previously “Contribution Collection” ) module | Delivered
1.3 | Frontend module for the “Policy Holder Portal” | April 28, 2021
1.4 | Frontend for the “Contract” (previously “Contribution Collection” ) module | Delivered
2.1 | Frontend and backend for the “Contribution plan and Contribution plans bundle” module | Delivered
2.2 | Frontend and backend for the “Calculation” module | Delivered
3 | Frontend and backend the “Profile” module | Delivered
4.1 | Early delivery of the Shell backend modules (“Policy holder”, “Contribution Collection”, “Contribution plans” ), | Delivered
4.2 | reviewed Healthix FIHR documents | Delivered

## Slide 6: Formal sector
Review meeting
GIZ. 574327-01706501-CRT
14th January 2021

## Slide 7: Agenda
Presentation of the contract module (Deliverable 1.4 and 1.2)
  Create contract
  Copy of the PH Insuree parameter on Contract Details
  Edit policy details (create/edit/update/delete)
  Submit contract
  Approve Contract
  See policies
  Delete/update contract
Presentation of the Calculation module (Deliverable 2.2)
  Assign calculation to contributionPlan
  Change calculation parameters in contributionPlan
  Change calculation parameters in contractDetails
  See impact of calculation on contract value

## Slide 8: Presentation of the contract module
  https://modular.fs.swisstph-mis.ch/
UC3-10: add Contract
UC3-2: Add contract from PH
UC3-11: Access to contract
UC3-12: Access to a contract via PolicyHolder
UC3-3: Update contract details
UC3-3.1: add contractDetail
UC3-3.2: Update contractDetails
UC3-3.3: Dupdate delete contract detail
UC3-4: Submit contract
UC3-13: Approve Contract
UC3-13.1: see contribution plan details
UC3-6: Counter Contract
UC3-7: Amend contract
UC3-X: Delete contract

## Slide 9: Presentation of the Calculation module
UC14-1: add a new Calculation rule (needs to change the openimis.json). UC14-2: be able to select a calculation rule. UC14-3: display in editable mode the parameters required by calculation for an object. UC14-4: replace a calculation rule. (python change) UC14-5: remove a calculation rule. (python change)

## Slide 10: Presentation of the Profile module
Add profile
Remove profile
Duplicate profile
Edit profile
Search profile

## Slide 11: Next steps
Even if we ask for the acceptance of the module we will keep working on them:
  Fix defect when they will be detected