## Slide 1: AI-based Claim Categorization
7 June 2021

## Slide 2: Project timeline
Activity |  | Team | 2020 |  |  | 2021 | 
 |  |  | Jun-Jul | Aug-Sep | Oct-Dec | Jan-Mar | April
Data gathering and preparation | AI input data model structure | Swiss TPH | X |  |  |  | 
 | FHIR claim input data for AI | Swiss TPH | X |  |  |  | 
 | Sanity check of the database | Swiss TPH |  | X |  |  | 
 | Process categorical data | Swiss TPH |  | X |  |  | 
 | Data normalization | Swiss TPH |  | X |  |  | 
Implementation of the AI algorithm | Al methods, model outputs and evaluation metrics | Swiss TPH |  |  | X |  | 
 | Development of the AI model | Swiss TPH |  |  |  | X | 
AI-based Claim Adjudication Process |  | Swiss TPH |  |  | X |  | 
openIMIS Claim-AI module development | Claim-AI module specification | Swiss TPH |  |  | X |  | 
 | Claim-AI module development | SolDevelo |  |  |  | X | 
 | Claim-AI module validation | Swiss TPH |  |  |  | X | 
openIMIS Claim-AI Quality Monitor module development | Claim-AI Quality Module specification | Swiss TPH |  |  | X |  | 
 | Claim-AI Quality Module development | SolDevelo |  |  |  | X | 
 | Claim-AI Quality Module validation | Swiss TPH |  |  |  | X | 
Module User Acceptance Testing | Installation of AI-based openIMIS on Nepal server | SolDevelo |  |  |  |  | X
 | Organization of the UAT | GIZ Nepal |  |  |  |  | X

## Slide 3: Completed Activities
UAT Workshop
  Went well
  Limited feedback from Medical Officers  waiting for actual use in production
Received last NHIB database
Validation
  Discovered a degradation of the AI Model performance cause by data drift
Data drift is caused by
  COVID situation: data distribution before and after is not the same
  Categorical field proportion more than 60%
Ways to improve
  Solve data drift issues by creating aggregated field  requires access to full DB, meaning a copy of the FHIR data on AI module implementation
  Improve label consistency
Insurlab participation
  Limited feedback  waiting for follow up meetings (?)

## Slide 4: AI-based Claim Categorization