## Slide 1: Implementation of the openIMIS for the HIV User Fees Exemption Project

## Slide 2: Introduction
In April 2019, Cameroon's Ministry of Public Health issued a landmark ministerial decision, No. 0498, establishing that a range of services are provided free of charge at public facilities and community based sites for HIV testing and treatment
Fee removal is a bold policy move that has the potential to improve coverage, access, and equity of services delivery and accelerate progress toward achieving the goals of HIV response

## Slide 3: Introduction
Well-defined operational processes and appropriate tools for project implementation are important to avoid unintended effects and undermine the expected positive impact of the policy decision
The MOPH has identified openIMIS as a possible tool that can be customized to meet the business processes as defined by the Standard Operating Procedures (SOPs) of Cameroon's free HIV services program

## Slide 4: Introduction
The MOPH requested support for the pilot implementation of the openIMIS software for the HIV user fees project
There are two regions where OpenIMIS is piloted: North West and Center regions
The users from the Regional Funds and health facilities have been trained for the implementation

## Slide 5: Status of the Pilot Phase

## Slide 6: Status of the Pilot Phase
Trainers have been trained at the Central and Regional levels on the openIMIS software
These trainers supported the training of focal persons in pilot Health Facilities in the Center the North West Region
There are 27 Health facilities in the North West region and 27 in the Center region participating
An openIMIS Consultant was hired to support the implementation of openIMIS for the project while a local IT company was hired to customize the tool and provide technical support and assistance for the two pilot Regions

## Slide 7: Results of the implementation of the openIMIS software in the selected Regions (Center and Northwest)

## Slide 8: Results of the implementation of the openIMIS software in the selected Regions
The pilot phase was to test the feasibility and value addition of the openIMIS tool in generating health bills for reimbursement for the HIV user fees exemption project
It was observed that the tool can be implemented effectively and has added value to the project especially for the Regional Funds as it leads to the timely generation of health bills and to the Ministry of Public Health as it leads to efficiency, effectiveness, traceability and the elimination of fraud to achieve the objectives of the project through the effective utilization of public funds to meet the needs of the population

## Slide 9: Difficulties Encountered

## Slide 10: Difficulties Encountered
Lack of computers in most health facilities dedicated to data entry and invoice generation via openIMIS
Frequent replacement of Data Managers who have been trained in openIMIS
Lack of internet credit for Data Managers who enter data and generate invoices for Health Facilities from openIMIS

## Slide 11: Conclusion

## Slide 12: Conclusion
The pilot is interesting because the tool:
  Ensures the availability and accuracy of information
  Accelerates the speed of operations and controls
  Reduce fraud and thus achieve efficiency in the use of the government subsidy

## Slide 13
MERCI