## Slide 1: Modular Migration Roadmap
openIMIS Gumzo
07.03.2022

## Slide 2: Refresher
Modular Migration

## Slide 3: Progress Modular Re-architecture
Chart: 
| Done (Tender 3 2018) | Done (Digital Square 2019) | Doing (Tender 3 2020)
Column2 | 1 | 1 | 1
Aim:
Pure open source software stack
Scope:
Modules needed for new implementations
Migration of special local features might still be needed
Targets:
Database switch mid 2022
Release in October 2022

## Slide 4: Slow Transition (2021 roadmap)
MS IMIS
Framework
openIMIS
Claiming, Locations, Enrollment, Policy, Contributions
Payers, Adm. Tools, Reps
April 2019
Oct. 2019
April 2020
Releases:
Claims Adjudication - AI
Formal Sector, Accident Insurance
Oct. 2020
April 2021
new
Users, Items, Services, Pricelists
Oct. 2021
Payment Layer
April 2022
Oct. 2022
openHIE Integration (FHIR), Indicator Dashboard (DHIS2)
Database

## Slide 5: Roadmap: Things to Think about
Remaining legacy functions (as known today)
  REST API (mobile apps), country specific tweaks
Tender process for new maintenance contract
  Pure modular version or hybrid? -> applicants profiles
Communication to implementations
  Critical period after 2022-08 (end of support for legacy version)
  Grace period of 6 months after first pure OS release (in-country migration of missing functionality into core)

## Slide 6: Phase out Legacy Version
GIZ S2HS (NP)
Maintenance N.N.
Tender
MS IMIS
19-04
19-10
20-04
Releases:
20-10
21-04
21-10
22-04
23-04
22-10
23-10
openIMIS
2019
2020
SwissTPH
GIZ (DE)
BlueSquare
funded
unfunded
2023
2021
2022
responsibility in countries
2023-08
2022-08

## Slide 7: Brainstorming
Roadmap

## Slide 8: Co-ordination Desk Activities
2023
2022
Maintenance N.N.
Maint. SwissTPH
MS IMIS
22-04
23-04
22-10
23-10
openIMIS
In-country problem
2023-08
2022-08
TORs
GIZ (DE)
unfunded
unfunded
tender process
sign
monitor
pay
assess existing imps
plan doc update
plan next phase
communicate nxt phs
define funds for 2024

## Slide 9: Implementer Committee Activities
2023
2022
Maintenance N.N.
Maint. SwissTPH
MS IMIS
22-04
23-04
22-10
23-10
openIMIS
In-country problem
2023-08
2022-08
GIZ (DE)
unfunded
unfunded
update training material
explore on Demo
Assess training material
update test cases

## Slide 10: Developer Committee Activities
2023
2022
Maintenance N.N.
Maint. SwissTPH
MS IMIS
22-04
23-04
22-10
23-10
openIMIS
In-country problem
2023-08
2022-08
GIZ (DE)
unfunded
unfunded
update test cases

## Slide 11: Activities in Countries
2023
2022
Maintenance N.N.
Maint. SwissTPH
MS IMIS
22-04
23-04
22-10
23-10
openIMIS
In-country problem
2023-08
2022-08
migrate country specific tweaks
pilot
train
test
roll-out
pilot
train
test
roll-out
GIZ (DE)
unfunded
unfunded
explore on Demo

## Slide 12: Communication Activities
2023
2022
Maintenance N.N.
Maint. SwissTPH
MS IMIS
22-04
23-04
22-10
23-10
openIMIS
In-country problem
2023-08
2022-08
GIZ (DE)
unfunded
unfunded
communicate exploration phase
communicate roadmap
celebrate
inform about pure OS

## Slide 13: Potential Funding Opportunities
2023
2022
Maintenance N.N.
Maint. SwissTPH
MS IMIS
22-04
23-04
22-10
23-10
openIMIS
In-country problem
2023-08
2022-08
GIZ (DE)
unfunded
unfunded
German DC (Health, Digital, Social Protection)
Digital Convergence Initiative in Social Protection
GovStack
Manna Funds
Implementations
Manna Funds
Implementations
Implementations
Implementations
DSq Notice F

## Slide 14: Colour scheme
0
0
0
Dark 1
255
255
255
Light 1
79
75
76
Dark 2
169
167
168
Light 2
0
99
116
Accent 1
128
176
185
Accent 2
244
174
43
Accent 3
248
233
70
Accent 4
200
15
15
Accent 5
164
160
208
Accent 6
Chart: 
| Accent 1 | Accent 2 | Accent 3 | Accent 4 | Accent 5 | Accent 6
Farbe | 20 | 20 | 20 | 15 | 10 | 15